## Plan isporuke
BOOKSY — Plan isporuke po sprintovima
Kolegij: Oblikovanje i izrada cjelovitog aplikacijskog rješenja ¦ Tim: Kondža, Dronjić, Nardiello, Jerković
Sprint | Trajanje | Cilj sprinta | Zadaci | Odgovoran | Status | Napomena
Sprint 1 | 18.03. – 01.04.2026. | Početak projekta i postavljanje temelja | Početak projekta i okupljanje tima | Cijeli tim | Završeno
|  |  | Kratki opis projekta | Kondža (PM)
|  |  | Plan isporuke (ovaj dokument) | Kondža (PM)
|  |  | Postavljanje razvojnog okruženja | Cijeli tim
|  |  | Dizajniranje arhitekture sustava | Dronjić, Kondža
|  |  | Dizajn baze podataka (PostgreSQL) | Dronjić, Kondža
Sprint 2 | 02.04. – 15.04.2026. | Izrada backenda — autentifikacija i baza | Postavljanje Spring Boot projekta | Kondža (PM) | Završeno
|  |  | Spajanje na Railway PostgreSQL bazu | Kondža (PM)
|  |  | Kreiranje JPA entiteta (sve tablice) | Kondža (PM)
|  |  | REST API — User (registracija, prijava) | Kondža (PM)
|  |  | JWT autentifikacija i autorizacija | Dronjić
|  |  | Swagger / OpenAPI dokumentacija | Dronjić
Sprint 3 | 16.04. – 29.04.2026. | Backend — property, rezervacije + početak weba i androida | REST API — Property i User_Property (admin flow) | Dronjić | U tijeku
|  |  | REST API — Room (CRUD) | Dronjić
|  |  | REST API — Reservation (CRUD, statusi) | Dronjić
|  |  | REST API — Review | Dronjić
|  |  | Početak web sučelja — login, dashboard | Jerković
|  |  | Početak Android app — login, registracija | Nardiello, Kondža
Sprint 4 | 30.04. – 13.05.2026. | Web admin sučelje + Android core funkcionalnosti | Web — upravljanje propertyima i sobama | Jerković | Planirano
|  |  | Web — pregled i upravljanje rezervacijama | Jerković
|  |  | Web — admin odobravanje propertyia | Jerković
|  |  | Android — pretraga apartmana i detalji | Nardiello, Kondža
|  |  | Android — rezervacija sobe | Nardiello, Kondža
|  |  | Android — prikaz mojih rezervacija | Nardiello, Kondža
Sprint 5 | 14.05. – 27.05.2026. | Notifikacije, recenzije i integracijsko testiranje | Firebase Cloud Messaging — push notifikacije | Dronjić | Planirano
|  |  | Android — recenzije i ocjene | Nardiello, Kondža
|  |  | Web — statistika i analitika | Jerković
|  |  | Integracijsko testiranje (Postman) | Cijeli tim
|  |  | Ispravak bugova s testiranja | Cijeli tim
|  |  | Docker — kontejnerizacija aplikacije | Dronjić
Sprint 6 | 28.05. – 10.06.2026. | Završno testiranje, dokumentacija i prezentacija | End-to-end testiranje cijelog sustava | Cijeli tim | Planirano
|  |  | GitHub Actions CI/CD pipeline | Dronjić
|  |  | Završna dokumentacija projekta | Kondža (PM)
|  |  | Priprema prezentacije | Cijeli tim
|  |  | Demo aplikacije | Cijeli tim
|  |  | Predaja projekta | Kondža (PM)

## SQL Shema
-- ============================================================
-- BOOKSY DATABASE SCHEMA
-- PostgreSQL (Railway)
-- ============================================================
-- 1. USER
CREATE TABLE "user" (
id SERIAL PRIMARY KEY,
first_name VARCHAR(100) NOT NULL,
last_name VARCHAR(100) NOT NULL,
email VARCHAR(255) NOT NULL UNIQUE,
password VARCHAR(255) NOT NULL,
role VARCHAR(20) NOT NULL DEFAULT 'GUEST',
-- GUEST ¦ OWNER ¦ ADMIN
created_at TIMESTAMP NOT NULL DEFAULT NOW()
);
-- 2. PROPERTY
-- owner_id je NULL dok admin ne odobri zahtjev
CREATE TABLE property (
id SERIAL PRIMARY KEY,
owner_id INT REFERENCES "user"(id),
-- NULL dok nije odobreno
name VARCHAR(255) NOT NULL,
address VARCHAR(255) NOT NULL,
city VARCHAR(100) NOT NULL,
country VARCHAR(100) NOT NULL
);
-- 3. USER_PROPERTY (zahtjev vlasnika za property)
-- Owner submita, admin odobrava -> owner_id se upisuje u property
CREATE TABLE user_property (
id SERIAL PRIMARY KEY,
user_id INT NOT NULL REFERENCES "user"(id),
property_id INT NOT NULL REFERENCES property(id),
status VARCHAR(20) NOT NULL DEFAULT 'PENDING',
-- PENDING ¦ ACCEPTED ¦ DENIED
requested_at TIMESTAMP NOT NULL DEFAULT NOW(),
reviewed_at TIMESTAMP
);
-- 4. ROOM
CREATE TABLE room (
id SERIAL PRIMARY KEY,
property_id INT NOT NULL REFERENCES property(id),
name VARCHAR(100) NOT NULL,
capacity INT NOT NULL DEFAULT 2,
price_per_night DECIMAL(10,2) NOT NULL,
available_from DATE NOT NULL,
available_to DATE NOT NULL,
CONSTRAINT chk_room_dates CHECK (available_to > available_from)
);
-- 5. RESERVATION
CREATE TABLE reservation (
id SERIAL PRIMARY KEY,
guest_id INT NOT NULL REFERENCES "user"(id),
room_id INT NOT NULL REFERENCES room(id),
check_in DATE NOT NULL,
check_out DATE,
total_price DECIMAL(10,2) NOT NULL,
status VARCHAR(20) NOT NULL DEFAULT 'PENDING',
-- PENDING ¦ ACCEPTED ¦ DENIED
created_at TIMESTAMP NOT NULL DEFAULT NOW(),
CONSTRAINT chk_res_dates CHECK (check_out > check_in)
);
-- 6. REVIEW
CREATE TABLE review (
id SERIAL PRIMARY KEY,
reservation_id INT NOT NULL REFERENCES reservation(id),
rating INT NOT NULL,
comment VARCHAR NOT NULL,
created_at TIMESTAMP NOT NULL DEFAULT NOW(),
CONSTRAINT chk_rating CHECK (rating BETWEEN 1 AND 5),
CONSTRAINT uq_res_review UNIQUE (reservation_id)
-- 1 recenzija po rezervaciji
);

## Tim
BOOKSY — Tim projekta
Ime i prezime | Uloga | Odgovornosti
Hrvoje Kondža | Projekt menadžer / Backend | Vođenje projekta, backend (Spring Boot), koordinacija tima
Tomislav Dronjić | Backend developer | Spring Boot, REST API, baza podataka, Docker
Leonardo Nardiello | Android developer | Kotlin Android app, Retrofit, UI
Ivan Jerković | Web developer | HTML/CSS/JS frontend, web admin sučelje